## Daily_SEO_Action_Tracker
S.No | Task ka Naam | Target Page (URL & File Path) | Target Keywords | Reason (Kyu kiya gaya?) | Result kab check karna hai (Timeline & Action) | Review / Result Date | Lock Status (Cooldown) | Action / Status
01 | Robots.txt Optimization | /robots.txt (src/app/robots.ts) | Sitewide AI Crawlers (GPTBot, PerplexityBot, ClaudeBot, Googlebot) | AI search engines aur Googlebot ko site ke sabhi B2B pages crawl karne ki permission di, sensitive API routes block kiye. | 24 se 48 ghante me -> GSC Settings > Crawl Stats me verify karein. | 2026-09-25 (+48 hrs) | LOCKED UNTIL REVIEW | Done / Pending Review
02 | Dynamic Sitemap Generation | /sitemap.xml (src/app/sitemap.ts) | Sitewide 75+ Dynamic URLs (Pillars, Products, Insights) | Googlebot ko sabhi landing pages aur 64+ product URLs ka structured map diya taaki crawl budget maximize ho. | 24 se 48 ghante me -> GSC Sitemaps tab me 'Success' aur 75+ Discovered URLs check karein. | 2026-09-25 (+48 hrs) | LOCKED UNTIL REVIEW | Done / Pending Review
03 | Global Entity Schema Graph | Entire Site Layout (src/app/layout.tsx) | SMD Life Sciences, IVD raw materials India, Biotech company Bangalore | Google Knowledge Graph me SMD Life Sciences ko Bangalore-based verified biotech manufacturer ke roop me register karne ke liye. | 7 se 14 din me -> Google Rich Results Test aur Knowledge panel verification. | 2026-10-07 (+14 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
04 | Commercial Pillar #1 | /ivd-raw-materials (src/app/ivd-raw-materials/page.tsx) | • IVD raw materials India • IVD raw materials manufacturer • lateral flow raw materials • bulk diagnostic antigens India | Domestic diagnostic kit manufacturers ke high-intent B2B procurement queries ko direct landing page par capture karna. | 3 se 5 din me (Indexing) 15 se 30 din me (Rankings) -> GSC Performance > Pages me impressions track karein. | 2026-10-23 (+30 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
05 | Commercial Pillar #2 | /recombinant-antigens (src/app/recombinant-antigens/page.tsx) | • recombinant antigens manufacturer Bangalore • recombinant antigens India • custom antigen expression India • bulk recombinant proteins IVD | High-margin procurement keywords capture karna aur Bangalore biomanufacturing facility trust build karke RFQs drive karna. | 3 se 5 din me (Indexing) 15 se 30 din me (Rankings) -> GSC queries me Bangalore local keyword ranking check karein. | 2026-10-23 (+30 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
06 | Commercial Pillar #3 | /diagnostic-cdmo (src/app/diagnostic-cdmo/page.tsx) | • diagnostic CDMO • IVD CDMO services India • lateral flow contract manufacturing • rapid test contract manufacturing Bangalore | Blue Ocean B2B keyword ko dominate karna jahan koi doosri Indian diagnostic firm complete CDMO claim nahi kar rahi. | 3 se 5 din me (Indexing) 2 se 4 hafte me (Inbound RFQs) -> RFQ submissions aur GSC query clicks monitor karein. | 2026-10-21 (+28 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
07 | Homepage FAQ & Accordion Schema | / (src/app/page.tsx) | • SMD Life Sciences Bangalore • IVD diagnostic solutions • recombinant proteins manufacturer | Native <details> tag se zero CLS aur FAQPage schema se Google/Perplexity AI me direct answer snippets pane ke liye. | 3 se 7 din me -> GSC Enhancements > FAQ aur search rich snippets me check karein. | 2026-09-30 (+7 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
08 | Product Datasheets Mesh & B2B RFQ | /products/[code] (64+ Catalog Reagents) | • dengue ns1 antigen bulk • malaria pf pv antigen • troponin i antibody bulk • HIV recombinant antigen • salmonella typhi antigen | price: '0' penalty trap hataya, B2B RFQ button diya aur related antigens ka internal mesh banaya taaki koi dead-end page na rahe. | 5 se 7 din me -> GSC Product Snippets / Merchant Listings me zero errors verify karein. | 2026-09-30 (+7 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
09 | SEO-Friendly 404 Recovery Page | /not-found (src/app/not-found.tsx) | Site Recovery & Navigation (Brand Terms) | Dead links par aane wale crawlers aur users ko bounce hone se rokna aur crawl budget waste hone se bachana. | Immediate / Ongoing -> GSC Pages > Not Found (404) report me soft-404 monitor karein. | 2026-09-24 (+24 hrs) | LOCKED UNTIL REVIEW | Done / Pending Review
10 | GSC Priority Indexing Submission | • / • /ivd-raw-materials • /recombinant-antigens • /diagnostic-cdmo | All Core Priority Commercial & Local Keywords | Googlebot ko fast-track priority crawl queue me signal dena taaki naye pages bina wait kiye SERP me list hon. | 24 se 72 ghante me -> GSC URL inspection me 'URL is on Google' green tick check karein. | 2026-09-26 (+72 hrs) | LOCKED UNTIL REVIEW | Done / Pending Review
11 | Scientific Whitepaper / Blog #1 | /insights/reducing-batch-to-batch-variation-lateral-flow-assays | • batch to batch variation lateral flow assay • lot to lot variation diagnostic assay • recombinant antigen quality for IVD • antigen purity lateral flow test line • carrier free recombinant antigens | R&D heads ke #1 pain point ko solve karke high topical authority (E-E-A-T) build karna aur 3 commercial pillars ko backlink dena. | 3 se 5 din me (Indexing) 14 se 21 din me (Rankings) -> Scientific & problem-solving queries par impressions check karein. | 2026-10-14 (+21 Days) | LOCKED UNTIL REVIEW | Done / Pending Review
12 | WebP 3D Visual Banner Pipeline | /images/insights/lateral-flow-variation-antigen-quality.webp | • lateral flow assay diagram • lateral flow test strip architecture • nitrocellulose membrane test line | Broken image icon fix karna, Core Web Vitals (LCP < 1.2s) optimize karna, aur Google Images tab me visual ranking lena. | Immediate / 24 ghante me -> PageSpeed Insights (LCP score) aur Google Image Search me check karein. | 2026-09-24 (+24 hrs) | LOCKED UNTIL REVIEW | Done / Pending Review